## Sheet1
Risk | Description | Risk Level | Analysis
Incompletion of all methods | Not all required functions (move validation, capture logic, king promotion, win detection, board display) may be fully implemented within the short timeline. Missing methods will cause major portions of the game to break. | High | The team must prioritize core gameplay features first, implement methods in small testable pieces, and avoid starting optional features before required mechanics are complete. Daily progress checks are essential.
Methods don’t write or read from files | Save/load features, logs, or debugging file operations may fail due to incorrect file handling or path errors. This can prevent saving game state or reading configuration data. | Medium | Ensure file operations use correct paths and permissions. Test writing and reading early, use simple text formatting, and validate file existence before reading. Implement error-checking around file streams.
Game Loop doesn’t Loop properly | The main loop may prematurely exit, loop infinitely, or fail to alternate turns correctly. This will prevent the game from progressing or responding to inputs. | High | Break the loop into clear stages: input → validation → update → render → turn switch. Test the loop with mock moves before adding full logic. Add safe exit conditions to prevent infinite loops.
Players don’t know rules of the game or how to input moves into the game | Without clear instructions, players may enter invalid commands, misunderstand move formatting, or be unaware of legal Checkers rules. This leads to user errors and confusion. | Medium | Provide clear on-screen instructions, examples of valid inputs, and error messages. The user manual should include move examples and explanations of rules. Add input validation to guide players.
Game board matrix misalignment | The 8×8 board array may display incorrectly, causing visual errors such as shifted rows/columns or mismatched coordinates. This makes gameplay confusing or unplayable. | Medium | Test board rendering early. Print row/column labels, ensure loop indices match the visual grid, and validate that display formatting remains consistent after each move.
Task Title | Task Owner | Start Date | Due Date | Task Complete
Checkers Game System Requirements | Jayden Brooks | 2025-11-30 | 2025-12-20 | Complete
hardware requirements | Jayden Brooks | 2025-11-30 | 2025-12-20 | Complete
Function // Class // Variable Outline
ASCII Art Read File Writing
ASCII Art Read File Testing
Function Definition and Writing
Function Testing
Class Definition and Writing
Class Testing
File Write Function Writing
File Write Function Testing